## Master Plan
HLC Sales Execution Calendar — 1 to 23 October 2026
Day 0 = Thu 1 Oct (Niharika joins). Weekends and holidays (2 Oct, 19 Oct) are non-working. 12 working days to Vijayadasami. Targets: 20 KG + 10 Grade 1 seats from 200 leads.
Workstream | ID | Activity | Owner | Start day | Start date | Due day | Due date | Output | Milestone | Status
0 Orientation
0 Orientation | O1 | Self-enablement plan — see HLC_Growth_Leader_Orientation.xlsx | Niharika | 0 | 2026-10-01 | 5 | 2026-10-09 | Orientation pack | ★ M0 | Not started
1 Foundation
1 Foundation | F1 | Thank-you note to every family, with alumni proof points | Founders + Niharika | 0 | 2026-10-01 | 1 | 2026-10-05 | Sent to all families | ★ M1 | Not started
1 Foundation | F2 | Website live: seat counts, one-field enquiry form, Vidyarambham invite | Niharika + web vendor | 0 | 2026-10-01 | 2 | 2026-10-06 | Live page | ★ M2 | Not started
1 Foundation | F3 | Enquiry tracker and daily scorecard set up (Google Sheet) | Niharika | 0 | 2026-10-01 | 1 | 2026-10-05 | Tracker live |  | Not started
1 Foundation | F4 | HLC Discover quick wins: signage, KG toilet tour-ready, Circle of Three tops and badges, photo wall | KG coordinator | 1 | 2026-10-05 | 5 | 2026-10-09 | Campus tour-ready | ★ M4 | Not started
1 Foundation | F5 | Google Business listing: HLC Discover — the early years of HLC International | Niharika | 1 | 2026-10-05 | 3 | 2026-10-07 | Listing live |  | Not started
1 Foundation | F6 | Hire three field staff for one month: two outreach, one logistics | Founders | 1 | 2026-10-05 | 4 | 2026-10-08 | Staff in place |  | Not started
2 Warm list
2 Warm list | W1 | Build the returning-families list (≈85), checked against admissions records | Niharika + admissions | 0 | 2026-10-01 | 1 | 2026-10-05 | Clean call list |  | Not started
2 Warm list | W2 | Call returning families with the early-bird offer — 15 a day | Niharika | 1 | 2026-10-05 | 6 | 2026-10-12 | All ≈85 contacted | ★ M5 | Not started
2 Warm list | W3 | Founders call current families with a younger child, and alumni families | Founders | 1 | 2026-10-05 | 8 | 2026-10-14 | All called |  | Not started
3 Community
3 Community | C1 | Recruit one parent ambassador in each of the six hotspot communities | Niharika + founders | 1 | 2026-10-05 | 4 | 2026-10-08 | 6 ambassadors | ★ M3 | Not started
3 Community | C2 | Golu invitations: 20–30 crafted with gift; e-invite design for all | Logistics staff | 2 | 2026-10-06 | 5 | 2026-10-09 | Invites ready |  | Not started
3 Community | C4 | A3 posters in communities, with association permission | Outreach staff | 3 | 2026-10-07 | 7 | 2026-10-13 | Posters up |  | Not started
3 Community | C3 | Distribute invitations; e-invites shared by every family | Ambassadors + staff | 5 | 2026-10-09 | 8 | 2026-10-14 | Invites out |  | Not started
3 Community | C5 | Navaratri play corner in hotspot communities (weekday dates; weekend only with founder approval) | Niharika + ambassadors | 6 | 2026-10-12 | 10 | 2026-10-16 | 2–3 corners run |  | Not started
3 Community | C6 | HLC golu on campus for the neighbourhood | KG team | 8 | 2026-10-14 | 8 | 2026-10-14 | Golu held |  | Not started
4 Grade 1
4 Grade 1 | G1 | "Ready for Real School" one-page checklist for UKG parents | Niharika + Grade 1 teacher | 2 | 2026-10-06 | 4 | 2026-10-08 | PDF ready |  | Not started
4 Grade 1 | G4 | Search ads: "Grade 1 admission near me", 5 km | Niharika | 3 | 2026-10-07 | 11 | 2026-10-20 | Ads live |  | Not started
4 Grade 1 | G2 | Share the checklist through community WhatsApp groups and ambassadors | Ambassadors | 5 | 2026-10-09 | 11 | 2026-10-20 | Shared widely |  | Not started
4 Grade 1 | G3 | "Ready for Real School" weekday session, 3:30–5 pm, open to any UKG child | Grade 1 team | 7 | 2026-10-13 | 9 | 2026-10-15 | Two sessions held | ★ M6 | Not started
5 Feeders
5 Feeders | P1 | List preschools within 5 km; invite their UKG parents to Ready for Real School | Outreach staff | 1 | 2026-10-05 | 2 | 2026-10-06 | List ready |  | Not started
5 Feeders | P2 | Founder visits to preschools, two a day; disclosed partnership where agreed | Founders | 3 | 2026-10-07 | 8 | 2026-10-14 | Visits done |  | Not started
6 Digital
6 Digital | D1 | WhatsApp status calendar — rotate campaign clips daily | Niharika | 1 | 2026-10-05 | 11 | 2026-10-20 | Daily posts |  | Not started
6 Digital | D2 | Geo-targeted Instagram and Meta ads, 5 km | Niharika | 3 | 2026-10-07 | 11 | 2026-10-20 | Ads live |  | Not started
7 Event
7 Event | E1 | Vidyarambham and open morning: three slots, tent, booking desks, early-bird | Founders + KG team | 3 | 2026-10-07 | 10 | 2026-10-16 | Event ready |  | Not started
7 Event | E2 | Registrations confirmed and reminders sent | Niharika | 9 | 2026-10-15 | 10 | 2026-10-16 | Final list | ★ M7 | Not started
7 Event | E3 | ★ Vijayadasami: Vidyarambham, golu, open morning, three slots | All | 11 | 2026-10-20 | 11 | 2026-10-20 | Admissions booked | ★ M8 | Not started
7 Event | E4 | Follow up every undecided family personally | Founders + Niharika | 12 | 2026-10-21 | 14 | 2026-10-23 | Closures |  | Not started
8 Review
8 Review | R1 | Daily scorecard, updated every evening | Niharika | 1 | 2026-10-05 | 14 | 2026-10-23 | Scorecard |  | Not started
8 Review | R2 | Checkpoint: KG enquiries ≥ 50 and Grade 1 ≥ 25, else add a community event and the mall activation | Founders + Niharika | 4 | 2026-10-08 | 4 | 2026-10-08 | Go / adjust | ★ Checkpoint | Not started
8 Review | R3 | Weekly review with founders | Founders + Niharika | 5 | 2026-10-09 | 10 | 2026-10-16 | Review notes |  | Not started

## Milestones
Quick wins and milestones
Each is a date the founders can check.
Milestone | Day | Date | What | Measure | Done?
★ M0 | 0 | 2026-10-01 | Orientation pack started | Deliverables in the orientation workbook
★ M1 | 1 | 2026-10-05 | Thank-you note sent to every family | 100% of families
★ M2 | 2 | 2026-10-06 | Website live with seat counts and form | Live
★ M3 | 4 | 2026-10-08 | Six hotspot ambassadors in place | 6
★ Checkpoint | 4 | 2026-10-08 | KG ≥ 50 and Grade 1 ≥ 25 enquiries | Go / adjust
★ M4 | 5 | 2026-10-09 | Campus tour-ready as HLC Discover | Signage, toilet, tops, photo wall
★ M5 | 6 | 2026-10-12 | All ≈85 returning families contacted | 85
★ M6 | 9 | 2026-10-15 | Two Ready for Real School sessions held | 2
★ M7 | 10 | 2026-10-16 | Vidyarambham registrations confirmed | Target 100 families
★ M8 | 11 | 2026-10-20 | Vijayadasami: 20 KG + 10 Grade 1 booked or in final follow-up | 30 seats

## Daily Scorecard
Daily scorecard
Enter each evening. Totals and gaps calculate automatically.
Day | Date | KG enquiries | Grade 1 enquiries | Visits | Applications | KG seats | Grade 1 seats
0 | 2026-10-01
1 | 2026-10-05
2 | 2026-10-06
3 | 2026-10-07
4 | 2026-10-08
5 | 2026-10-09
6 | 2026-10-12
7 | 2026-10-13
8 | 2026-10-14
9 | 2026-10-15
10 | 2026-10-16
11 | 2026-10-20
12 | 2026-10-21
13 | 2026-10-22
14 | 2026-10-23
Total |  | 0 | 0 | 0 | 0 | 0 | 0
Target |  | 135 | 65 | 105 | 45 | 20 | 10
Gap |  | 135 | 65 | 105 | 45 | 20 | 10