## Orientation Plan
Growth Leader Orientation — self-enablement, 1 to 9 October
Mornings: orientation. Afternoons: live sprint work. Founders give about 30 minutes a day. Pointed to from the Master Plan (O1).
Day | Date | Area | Activity | Who helps | Time | Output
0 | 2026-10-01 | a Internal | Founders 1:1 — HLC's story, philosophy and the three promises | Founders | 90 min | Notes for the fact card
0 | 2026-10-01 | d Plan | Read the internal playbook and the HLC Discover external deck | Self | 60 min | Questions list
0 | 2026-10-01 | a Internal | Read "Why We Do What We Do at HLC" | Self | 45 min | —
1 | 2026-10-05 | a Internal | Campus walk: KG block, Grade 1 classes, toilets, CCTV, entrance, pick-up | KG coordinator | 60 min | Tour notes
1 | 2026-10-05 | a Internal | Sit in one KG class and one Grade 1 class | Teachers | 60 min | Three moments to describe to parents
1 | 2026-10-05 | d Plan | Shadow a founder on five returning-family calls, then take over | Founder | Afternoon | Call script in her own words
2 | 2026-10-06 | a Internal | Meet Parent Connect, Learner Connect and the President's Award–winning teacher | Team | 60 min | Fact card complete
2 | 2026-10-06 | b Market | Drive the catchment: Thalambur, Karanai, Navalur, Sholinganallur, Perumbakkam, Padur, Siruseri | Self | Half day | Catchment map
2 | 2026-10-06 | d Plan | Walk-the-pyramid tour: rehearse with the KG coordinator | KG coordinator | 45 min | Tour script
3 | 2026-10-07 | c Competitor | Call five preschools as a parent: fees, hours, CCTV, apps, ratios | Self | Morning | Competitor sheet
3 | 2026-10-07 | c Competitor | Read websites and Google reviews: Billabong/Kangaroo Kids, Campus K, JS Global, PSBB OMR | Self | 60 min | Competitor sheet
3 | 2026-10-07 | b Market | Visit two hotspot communities with their ambassadors | Ambassadors | Afternoon | Contacts list
4 | 2026-10-08 | a Internal | Meet the governing council; meet five current parents | Founders | 60 min | Parent quotes
4 | 2026-10-08 | b Market | Read the Applicant Insights workbook: localities, reasons, profiles | Self | 45 min | Top five insights
4 | 2026-10-08 | d Plan | Draft the objection handbook: transport, CCTV, fee, hours, board | Self | 60 min | Objection handbook
5 | 2026-10-09 | a Internal | Student guides: two Grade 5 or 8 students show her their HLC | Students | 30 min | Stories for pitches
5 | 2026-10-09 | d Plan | Review with founders: pitches, handbook, scorecard; agree the rest of the sprint | Founders | 60 min | Orientation pack signed off
3 | 2026-10-07 | d Plan | Read the "Changing schools?" decks; learn the five switch reasons, walk a parent from their reason to their child's stage page, and close on the alumni proof | Self | 30 min | Switcher answer card
4 | 2026-10-08 | a Internal | Meet the Primary, Middle and Grade 11 coordinators: what switchers ask, how transitions work | Coordinators | 45 min | Transition notes

## Deliverables
Her reference pack — deliverables she keeps
Each one is hers to keep and improve through the year.
# | Deliverable | What it contains | Due day | Due date | Done?
1 | School fact card (one page) | Ratios, Circle of Three, faculty highlights, timings, fees, what's not offered (transport) | 1 | 2026-10-05
2 | 30-second and 3-minute pitches — KG and Grade 1 | In her own words, tested on two current parents | 3 | 2026-10-07
3 | Walk-the-pyramid tour script | Safe → Cared for → Learning → Loves learning; with stops on campus | 2 | 2026-10-06
4 | Catchment map | Localities, six hotspot communities, preschools and schools marked | 2 | 2026-10-06
5 | Competitor sheet | Ten rivals: fees, hours, CCTV, apps, ratios, where we win and lose | 3 | 2026-10-07
6 | Objection handbook | Fifteen questions and honest answers, incl. transport, live CCTV, fee, extended hours | 4 | 2026-10-08
7 | Contacts list | Ambassadors, association secretaries, preschool owners | 5 | 2026-10-09
8 | Her 90-day growth view | What she will do after 20 October to reach 100 admissions | 14 | 2026-10-23
9 | Switcher answer card | The five reasons families switch, our answer to each, and how a mid-year or June move works | 3 | 2026-10-07