HLC INTERNATIONAL SCHOOL INTERNAL OPERATIONS MANUAL

Multithemed BootCamp Integration Framework (Grades 5–12)

Version: 1.0
Prepared For: HLC International School Leadership & Faculty
Implementation Timeline: 6 Months (Phased Rollout)
Budget Requirement: Nil incremental cost (existing resources only)
Staff Requirement: Zero additional hiring (peer-led + teacher-integrated)

Executive Summary

This framework transforms existing school time into multithemed learning experiences without adding hours, staff, or budget. The model leverages:

| Resource | Current State | Repurposed Use |
| --- | --- | --- |
| Time | Existing periods + assembly + PTMs | Integrated exam prep + strategy sharing + wellness habits |
| People | Teachers + high-performing students | Subject facilitators + peer mentors (volunteer) |
| Space | Classrooms + library + notice boards | Same venues, reconfigured purpose |
| Budget | Nil additional | Zero cost (existing consumables redirected) |

Implementation Pecking Order (Grade Priority Sequence)

PHASE 1 (Months 1–2) → PHASE 2 (Months 3–4) → PHASE 3 (Months 5–6)

GRADES 10 & 12          GRADES 9 & 11           GRADES 5–8

(Critical Exam Focus)   (Foundation Building)   (Discovery & Culture)

Rationale: Grades 10 & 12 have highest parent ROI sensitivity + exam pressure. Success here creates proof points for school-wide scaling.

Detailed Operational Framework by Grade Band

GRADES 10 & 12: Critical Exam Integration (Priority 1)

| Component | Weekly Cadence | Duration | Facilitator | Location | Syllabus Integration |
| --- | --- | --- | --- | --- | --- |
| Morning Strategy Tip | Daily | 5 min | Rotating student volunteer | Main Assembly | No curriculum impact |
| Subject Simulation Blocks | 2×/week | 10 min per class | Subject teacher | Existing classroom | Replaces one practice question set |
| StrategySwap Forum | Bi-weekly | 60 min (after school, voluntary) | Senior peer mentor | Empty classroom | Student-led, optional attendance |
| Error Pattern Review | Weekly | 15 min (end of Friday class) | Subject teacher | Existing classroom | Part of regular assessment feedback |
| Wellness Check-in | Daily | 3 min | Self-guided (breathing exercise) | Anywhere | Pre-class transition |
| Peer Tutoring Slots | Voluntary | 30 min slots | Top 10% student volunteers | Library/classroom | Self-organized by students |
| Monthly Assembly Feature | Once/month | 5 min | Student volunteer + Principal | Main hall | Recognition of progress |
| Mistake Celebration | Once/month | 5 min | Rotating student speaker | Main assembly | Normalizing failure culture |

Sample Weekly Schedule (Grades 10 & 12)

┌────────────────────────────────────────────────────────────────────┐

│                    MONDAY                                         │

├────────────────────────────────────────────────────────────────────┤

│  8:30–8:45   Assembly: "Tip of Week" + Mistake Story              │

│  9:00–10:30  Math: Subject Deep Dive                              │

│  10:30–10:45 Break: Breathing Exercise (self-guided)               │

│  10:45–12:15 Science: Subject Deep Dive                           │

│  12:15–1:30  Lunch: Silent Study Zone (optional)                  │

│  1:30–2:30   Mock Paper Rotation (timed)                          │

│  2:30–3:30   StrategySwap Forum (voluntary, peer-led)             │

│  5:00–5:15   Daily Reflection Journaling (own notebook)           │

└────────────────────────────────────────────────────────────────────┘

┌────────────────────────────────────────────────────────────────────┐

│                    TUESDAY                                        │

├────────────────────────────────────────────────────────────────────┤

│  8:30–8:45   Assembly: Reminder + Peer Spotlight                 │

│  9:00–10:30  Languages: Exam Simulation Mode (10-min sprint)       │

│  10:30–12:15 Social Studies: Past Paper Analysis                  │

│  1:30–3:30   Peer Tutoring Slots (sign-up sheet at library)       │

└────────────────────────────────────────────────────────────────────┘

┌────────────────────────────────────────────────────────────────────┐

│                    WEDNESDAY                                      │

├────────────────────────────────────────────────────────────────────┤

│  8:30–8:45   Assembly: Strategy Tip #2                           │

│  9:00–12:15  Standard Syllabus Coverage (all subjects)             │

│  1:30–3:30   Optional: Peer-led Group Study                      │

└────────────────────────────────────────────────────────────────────┘

┌────────────────────────────────────────────────────────────────────┐

│                    THURSDAY                                       │

├────────────────────────────────────────────────────────────────────┤

│  8:30–8:45   Assembly: Student Question Submission               │

│  9:00–10:30  Weak Area Intensive (teacher identifies gaps)         │

│  10:30–12:15 Remediation Based on Error Logs                     │

│  1:30–3:30   Subject Deep Dive (Math/Science rotation)             │

└────────────────────────────────────────────────────────────────────┘

┌────────────────────────────────────────────────────────────────────┐

│                    FRIDAY                                         │

├────────────────────────────────────────────────────────────────────┤

│  8:30–8:45   Assembly: Mistake Celebration (volunteer student)     │

│  9:00–10:30  Full-Length Mock Paper (one subject)                 │

│  10:30–12:15 Error Analysis + Teacher Feedback                   │

│  1:30–2:30   StrategySwap Forum (weekly mandatory component)      │

│  2:30–2:45   Reflection & Week Wrap-up                            │

└────────────────────────────────────────────────────────────────────┘

Peer Mentor Selection Criteria (Grades 10 & 12)

| Criterion | Threshold | Verification |
| --- | --- | --- |
| Academic Standing | Top 10% of previous year's results | School records |
| Volunteering | Signed commitment to 2 hrs/week max | Simple form |
| Training | Attend 2-hour orientation by senior teacher | Attendance log |
| Rotation | Switch duties monthly to prevent burnout | Self-managed schedule |
| Recognition | Certificate + assembly mention + priority seating at events | Existing school channels |

GRADES 9 & 11: Foundation Building (Priority 2)

| Component | Weekly Cadence | Duration | Facilitator | Location |
| --- | --- | --- | --- | --- |
| Homework Help Circle | Weekly | 30 min | Peer mentor | Library |
| Subject Interest Clubs | Bi-weekly | 45 min | Interested student + teacher | Classroom |
| Career Pathway Preview | Monthly | 30 min | External speaker (volunteer) / Alumni | Auditorium |
| Mindfulness Moments | Daily | 3 min | Self-guided | All classes |
| Parent Education Add-on | Quarterly | 15 min (during PTM) | Admin staff | Existing PTM slot |

Note: Less intensive than Grades 10/12; focus is on building habits that prepare for exam years.

GRADES 5–8: Discovery & Culture (Priority 3)

| Component | Frequency | Duration | Facilitator | Purpose |
| --- | --- | --- | --- | --- |
| BrainSpark Activities | Monthly | 1 period/month | Subject teachers rotated | Creative problem-solving |
| Storytelling Circles | Monthly | 30 min | Language teacher | Communication skills |
| Math Games Tournament | Bi-monthly | 1 period | Math department | Making math engaging |
| Peer Buddy System | Ongoing | Self-paced | Paired students | Social support |

Purpose: Build school culture of collaboration and growth mindset before exam pressure hits.

Operational Workflow: Step-by-Step

Step 1: Stakeholder Alignment (Week 1–2)

| Action | Responsible Party | Timeline | Deliverable |
| --- | --- | --- | --- |
| Principal presentation to staff | Principal | Day 1–3 | Staff approval memo |
| Identify volunteer peer mentors | Grade coordinators | Day 3–7 | List of 15–20 students per critical grade |
| Draft simple peer mentor agreement | Admin | Day 5–7 | One-page commitment form |
| Create communication plan for parents | Marketing/Admin | Day 7–10 | WhatsApp script + email template |

Step 2: Pilot Launch (Week 3–6)

| Action | Responsible Party | Timeline | Deliverable |
| --- | --- | --- | --- |
| Conduct 2-hour peer mentor orientation | Senior teacher | Week 3 | Training completion list |
| Install notice board "Lessons Learned" corner | Office staff | Week 3 | Physical board ready |
| Share YouTube meditation playlist via WhatsApp | Admin | Week 4 | Link distributed to all parents/students |
| Begin Monday assembly strategy tips | Rotating student | Week 4 | First week completed |
| Launch StrategySwap Forum (Friday afternoons) | Grade 10/12 student lead | Week 4 | Attendance log started |

Step 3: Full Implementation (Month 2 onward)

| Action | Responsible Party | Timeline | Deliverable |
| --- | --- | --- | --- |
| Expand to Grades 9 & 11 | Grade coordinators | Month 2 | Same structure, lighter intensity |
| Gather informal feedback from students | Teachers | End of Month 2 | Anonymous feedback summary |
| Adjust frequency based on participation | Admin + Grade leads | Month 3 | Optimized schedule |

Step 4: Evaluation & Scaling (Month 4–6)

| Metric | Measurement Method | Target |
| --- | --- | --- |
| Participation rate in StrategySwap | Sign-in sheets | >60% of target grade |
| Peer tutor session attendance | Logbook | >50 students/week across grades |
| Parent satisfaction (informal) | PTM feedback forms | >80% positive comments |
| Exam performance trend | Internal assessments | 5–10% improvement vs. previous year |
| Student stress indicators | Anonymous survey (Google Forms) | 30% self-reported reduction |

Risk Management Matrix

| Risk | Probability | Impact | Mitigation Strategy | Responsible Party |
| --- | --- | --- | --- | --- |
| Peer mentor burnout | Medium | Medium | Max 2 hrs/week commitment; rotate monthly | Grade coordinator |
| Low StrategySwap attendance | Medium | Low | Make content appealing; student-led marketing | Senior student lead |
| Parent expectation mismatch | Medium | High | Clear communication: "supplemental, not guaranteed" | Principal + Admin |
| Exam prep conflicts with syllabus | Low | High | Integration only, no separate time | Subject department heads |
| Mistake sharing causes embarrassment | Low | Medium | Voluntary participation; anonymous option available | Counselor (if available) |
| Staff resistance to integration | Low | Medium | Frame as assessment efficiency, not added workload | Principal |

Resource Requirements (Actual Zero-Cost Breakdown)

| Item | Current School Asset Used | Additional Cost |
| --- | --- | --- |
| Classrooms | Already allocated | ₹0 |
| Library space | Already operational | ₹0 |
| Notice boards | Already installed | ₹0 |
| Assembly hall | Already scheduled | ₹0 |
| Notebooks for error logs | Students already own | ₹0 |
| YouTube playlists | Free platform | ₹0 |
| WhatsApp groups | Existing parent comms | ₹0 |
| Certificates for peer mentors | School already prints for events | ₹0 (redirect existing budget) |
| Printing (optional posters) | School print budget | ₹0–₹500 one-time (if needed) |
| Volunteer refreshments | Not required | ₹0 |

Total Additional Budget Required: ₹0

Success Metrics & Reporting cadence

| Metric | Frequency | Reporter | Recipient |
| --- | --- | --- | --- |
| Participation rates | Monthly | Grade coordinator | Principal |
| Student feedback summaries | Bi-monthly | Teacher liaison | Leadership team |
| Exam performance trends | Term-end | Academic head | Board/Founders |
| Parent sentiment analysis | Quarterly | Admin | Leadership team |

Appendix A: Templates (Zero-Cost Ready)

Peer Mentor Agreement Template

HLIC PEER MENTORSHIP COMMITMENT

I, [Student Name], Grade [X], voluntarily commit to:

□ Attend 2-hour orientation session

□ Dedicate maximum 2 hours/week to peer mentoring

□ Maintain confidentiality of peer learning sessions

□ Rotate responsibilities monthly to prevent burnout

□ Represent HLIC with professionalism and integrity

Signed: _________________ Date: ___/___/______

Parent Consent: _________________

Faculty Advisor Signature: _________________

StrategySwap Forum Agenda Template

STRATEGYSWAP FORUM — WEEK #___

Date: __________ Time: ______ Venue: ______

AGENDA (60 MINUTES TOTAL)

5 min    Welcome & Objective Setting

15 min   "One Technique That Worked For Me" Round Robin (3 students)

30 min   Open Q&A on Specific Exam Challenges

10 min   Collect Common Difficulties for Teacher Follow-up

Facilitator: _________________

Attendance Log: [Sign-in sheet attached]

Action Items for Next Week: _______________________